EXECUTION BLUEPRINT  |  CONFIDENTIAL  |  2025–2026

For Team Eyes Only — Not for Distribution

Alumni Compass Platform

From PRD to Working Product

Complete Team Execution Blueprint  |  6-Week Sprint Plan  |  Role-by-Role Ownership

| Document Type | Execution Blueprint + Sprint Plan |
| --- | --- |
| Team Size | 5 University Students |
| Timeline | 6 Weeks to Graduation Demo |
| Stack | React · Laravel · WebRTC · AI |
| Delivery Date | June 2026 |
| Classification | Internal – Team Only |

# Section 1 — Team Organization Chart

Five specialized roles designed for maximum parallel execution. No student owns everything; no student is idle. Each role maps to a clear domain with defined boundaries.

⚙️ Backend Lead Engineer Student 1 (S1) • Owns: Laravel API, Database schema, Authentication, Scheduling engine, Queue system • Makes architectural decisions for all server-side logic • Writes all API endpoints consumed by frontend and AI service • Reviews all backend pull requests before merge

🖥️ Frontend Lead Engineer Student 2 (S2) • Owns: React application architecture, routing, state management, API integration • Builds Graduate Dashboard, Mentor Dashboard, Booking flows • Consumes mock APIs first, switches to real APIs when backend is ready • Reviews all frontend pull requests before merge

🤖 AI & Systems Engineer Student 3 (S3) • Owns: Recommendation Engine (Python/FastAPI), CV ATS Scoring Engine, NLP pipeline • Builds WebRTC video session system and real-time WebSocket events • Exposes AI results as clean REST endpoints consumed by Laravel • Responsible for all smart feature logic and algorithm quality

🔗 Integration & QA Engineer Student 4 (S4) • Owns: API integration testing, end-to-end test flows, Admin Dashboard, deployment pipeline • Acts as the 'glue' — detects when frontend/backend/AI are misaligned and fixes the gap • Writes test scripts, manages staging environment, and runs pre-demo QA sprints • Owns the GitHub Actions CI/CD pipeline and deployment to Vercel + Railway

🎨 UI/UX Engineer + Frontend Support Student 5 (S5) • Owns: Design system (Tailwind + shadcn/ui), all UI components, Arabic RTL layout • Builds: Landing page, Onboarding wizard, CV Builder UI, Notification center • Supports S2 on complex frontend screens when needed • Responsible for mobile-first responsive layout and final visual polish

Leadership Note S1 and S2 are the two lead engineers. They make final technical decisions in their domain. S3 works semi-independently on AI — S1 wires AI into the Laravel backend. S4 catches integration bugs that no single developer would catch alone. S5 ensures the product looks and feels professional — critical for graduation demo impact.

# Section 2 — Task Distribution Matrix

Every module from the PRD is assigned to exactly one primary owner and one secondary support. This prevents duplication and ensures nobody is left without clear direction.

| Who | Role | Module Ownership | Key Deliverables | Tools |
| --- | --- | --- | --- | --- |
| S1 | Backend Lead | Auth & Roles, Session Booking, Scheduling Engine, Notifications (backend), Admin API | Auth API, Booking API, Scheduling logic, Admin API, DB migrations, Queue jobs | Laravel 11, PostgreSQL, Redis, Sanctum, Spatie Permission, Soketi |
| S2 | Frontend Lead | Graduate Dashboard, Mentor Dashboard, Booking UI, Messaging UI, Session History | All dashboard screens, Booking flow UI, Real-time chat UI, API integration layer | React 18, Vite, Zustand, Axios, React Hook Form, Laravel Echo |
| S3 | AI & Systems | AI Recommendation Engine, CV ATS Engine, NLP Pipeline, WebRTC Video System | FastAPI AI service, Recommendation scores, ATS scoring, WebRTC room component | Python, FastAPI, spaCy, scikit-learn, pdfplumber, LanguageTool API, WebRTC |
| S4 | Integration & QA | Admin Dashboard (UI), CI/CD Pipeline, End-to-End Testing, Deployment, API contracts | Admin Dashboard, GitHub Actions workflow, test reports, staging + production deploy | Vitest, Pest PHP, GitHub Actions, Railway, Vercel, Postman/Bruno |
| S5 | UI/UX + Frontend | Design System, Landing Page, Onboarding Wizard, CV Builder UI, Notifications UI | shadcn/ui component library, all form-heavy screens, Arabic RTL layout, mobile views | Tailwind CSS, shadcn/ui, Figma (free), React, i18next for Arabic |

## Module Ownership Quick Reference

| Platform Module | Primary Owner | Secondary Support |
| --- | --- | --- |
| 1. User Authentication & Roles | S1 — Backend Lead | S4 — Integration |
| 2. Graduate Dashboard | S2 — Frontend Lead | S5 — UI/UX Support |
| 3. Mentor Dashboard | S2 — Frontend Lead | S5 — UI/UX Support |
| 4. AI Mentor Recommendation Engine | S3 — AI Engineer | S1 — Backend (wiring) |
| 5. CV Builder + ATS Scoring Engine | S3 — AI Engineer | S5 — CV Builder UI |
| 6. Session Booking System | S1 — Backend Lead | S2 — Booking UI |
| 7. WebRTC Video Mentoring System | S3 — AI/Systems | S2 — Video room UI |
| 8. Notifications & Messaging | S1 — Backend (events) | S2 — Messaging UI |
| 9. Admin Dashboard | S4 — Integration/QA | S1 — Admin API |
| 10. API Integration Layer | S4 — Integration/QA | S1 + S2 coordination |
| 11. UI/UX & Frontend Design System | S5 — UI/UX Lead | S2 — Frontend Lead |
| 12. Deployment & Testing | S4 — QA Lead | All team |

# Section 3 — Detailed Responsibilities Per Student

## S1 — Backend Lead Engineer

Main Mission Build and own the entire Laravel backend: APIs, database, authentication, booking logic, notification events, and admin endpoints. You are the backbone of the entire system. Every other team member depends on your APIs being ready and documented on time.

### Daily Tasks & Weekly Goals

- DAILY: Write and document at least 2-3 API endpoints. Update API contract in Bruno/Postman collection shared with team.

- DAILY: Check Slack/Discord for frontend blockers — if S2/S5 are blocked on an API, it's your #1 priority.

- WEEK 1: Complete DB schema (all migrations), Auth API (register/login/OTP/roles), project scaffolding.

- WEEK 2: Mentor profile API, Availability slots API, Graduate profile API.

- WEEK 3: Booking system (create/confirm/cancel/conflict detection), Scheduling engine, reminder queue.

- WEEK 4: Notification events (WebSocket via Soketi), Messaging API, wire AI recommendation scores from S3's FastAPI into DB.

- WEEK 5: Admin API endpoints, performance optimization, fix integration bugs found by S4.

- WEEK 6: Final bug fixes, API documentation, deployment support.

### Final Deliverables — What Success Looks Like

- All 40+ REST API endpoints working and returning correct JSON per documented contract.

- Database fully seeded with demo data (10 mentors, 20 graduates, sample sessions, CVs).

- Auth flow works: Register → OTP → Login → Role-based access → Logout.

- Booking system: graduate books → mentor confirms → reminder fires → session completes.

- Laravel Queues processing notification jobs without manual intervention.

- AI service (S3) integrated: recommendation scores fetched and cached in Redis.

### Dependencies

- Gives to S2: Documented API endpoints (shared Bruno collection, updated daily).

- Gives to S3: DB schema for users/mentors/cvs, webhook to receive AI scores back.

- Gives to S4: API docs for integration testing, admin endpoints.

- Receives from S3: FastAPI base URL for AI service calls.

- Receives from S4: Bug reports from integration tests — fix within 24 hours.

## S2 — Frontend Lead Engineer

Main Mission Build the full React application: routing, state management, and all primary user-facing screens. You connect the backend (S1) and the design (S5) into a working product. You are responsible for the application feeling fast, correct, and integrated — not just visually complete.

### Daily Tasks & Weekly Goals

- DAILY: Work from mock API data initially — don't wait for backend. Switch to real APIs as S1 completes them.

- DAILY: Check S5's component library — use their components; never build UI from scratch.

- WEEK 1: React project setup (Vite, Zustand, React Router, Axios, i18next Arabic), base layout with RTL.

- WEEK 2: Graduate onboarding wizard (consume S5's wizard component), Mentor discovery page, Mentor profile page.

- WEEK 3: Booking flow (slot picker → confirm → success), Session history dashboard, Graduate dashboard home.

- WEEK 4: Mentor dashboard (availability manager, upcoming sessions), Real-time messaging UI (Laravel Echo), integrate WebRTC video room from S3.

- WEEK 5: Connect all pages to real APIs (replace mocks), fix all state management bugs, loading/error states.

- WEEK 6: Performance tuning, RTL review, final QA pass with S4.

### Final Deliverables — What Success Looks Like

- All 15+ screens implemented, connected to real APIs, loading correctly with real data.

- Arabic RTL layout working consistently on all screens.

- Real-time chat messages appear without page refresh (Laravel Echo WebSocket).

- Video session room loads, connects peers, shows video feed.

- All forms validate, show errors, and submit successfully to backend.

- No console errors on any page in the production build.

### Dependencies

- Receives from S1: API endpoints + Bruno collection. Blocks on: Auth API, Booking API, Profile APIs.

- Receives from S5: shadcn/ui components, design tokens, all reusable UI components.

- Receives from S3: WebRTC room component (drop-in React component with props: roomId, userId).

- Gives to S4: Working screens for QA testing; flagged UI bugs to be retested.

## S3 — AI & Systems Engineer

Main Mission Build two AI engines (Recommendation + ATS Scoring) and the video system (WebRTC). These are the features that will impress the graduation committee most. Focus on working implementations over academic perfection — a working 70% solution beats a broken 100% solution.

### Daily Tasks & Weekly Goals

- WEEK 1: FastAPI project setup, PostgreSQL connection, basic health endpoint. Plan the CV parsing pipeline. Read O*NET API docs.

- WEEK 2: Implement recommendation engine v1 (weighted cosine similarity — rule-based, no ML yet). Expose POST /recommend endpoint.

- WEEK 3: CV ATS Engine — PDF/DOCX parsing (pdfplumber + python-docx), keyword gap analysis against O*NET, ATS score formula. Expose POST /cv/analyze endpoint.

- WEEK 4: Grammar check integration (LanguageTool API), CV improvement suggestions. Begin WebRTC signaling server (integrate into Laravel Echo/Soketi via S1).

- WEEK 5: WebRTC video room React component — hand to S2 for integration. Test adaptive bitrate logic. Polish AI endpoints for demo quality.

- WEEK 6: Demo preparation — ensure all AI endpoints return realistic, impressive data for demo scenarios. Document all FastAPI endpoints.

### MVP Simplification Rules — Apply These

Simplify Without Shame Rule 1: Recommendation Engine = weighted scoring formula. NOT machine learning. That's fine. Rule 2: ATS Score = keyword matching + formatting rules. NOT deep NLP. That's fine. Rule 3: WebRTC = peer-to-peer video, Google STUN, Coturn TURN. NOT custom media servers. Rule 4: Grammar check = LanguageTool API (free). NOT a custom NLP model. The graduation committee will be impressed by a WORKING system, not theoretical complexity.

### Final Deliverables — What Success Looks Like

- FastAPI service running at /api/recommend — returns ranked mentor list with scores for any graduate profile.

- FastAPI service running at /api/cv/analyze — returns ATS score 0-100 + keyword gaps for any CV text.

- WebRTC video room works: two browser tabs connect, video streams display, audio transmits.

- Audio-only fallback activates when video quality degrades.

- All AI endpoints respond in under 3 seconds for demo scenarios.

### Dependencies

- Receives from S1: DB connection string, user/mentor schema (to build recommendation vectors).

- Gives to S1: FastAPI base URL, endpoint contracts for /recommend and /cv/analyze.

- Gives to S2: Drop-in WebRTC React component (VideoRoom.jsx) with documented props.

- Gives to S5: ATS score data structure so CV Builder UI can display it correctly.

## S4 — Integration & QA Engineer

Main Mission You are the quality guardian of the entire project. Your job is to find problems before the demo does. You also own the Admin Dashboard and the deployment pipeline — two high-visibility deliverables. Think like a user trying to break things, not a developer assuming things work.

### Daily Tasks & Weekly Goals

- WEEK 1: Set up GitHub Actions CI pipeline (lint + test on every PR). Set up staging environment (Railway + Vercel). Write API contract document as a shared reference for S1/S2.

- WEEK 2: Build Admin Dashboard UI (user list, mentor verification queue, basic stats). Test Auth API endpoints via Bruno. Document any discrepancies.

- WEEK 3: Build Admin analytics page. Write integration tests for Booking API flow. Run end-to-end flow: Register → Onboard → Find Mentor → Book → Confirm → Join Session.

- WEEK 4: Test AI endpoints (S3) — verify recommendation results and ATS scores. Test WebRTC video locally with S3. Run messaging flow tests.

- WEEK 5: Full regression test of every user journey. File bug reports in GitHub Issues. Coordinate with S1/S2/S3 on bug fixes. Deploy to production for first time.

- WEEK 6: Demo day preparation — rehearse demo flow 3 times with full team. Verify all demo accounts work. Write final test report.

### Final Deliverables — What Success Looks Like

- Admin Dashboard fully functional: list users, verify mentors, view session stats.

- GitHub Actions pipeline runs on every PR — catches broken tests before merge.

- Staging environment always running and accessible for team QA.

- Production deployment successful: platform accessible at real domain.

- Zero critical bugs in demo accounts/flows on graduation day.

- Demo data fully loaded: realistic mentor profiles, graduate accounts, completed sessions.

### Dependencies

- Receives from S1: Admin API endpoints, API docs.

- Receives from S2: Frontend screens to test against.

- Receives from S3: AI endpoint URLs to include in integration test suite.

- Gives to all: Bug reports (GitHub Issues) — clear reproduction steps, expected vs. actual.

- Gives to team: Deployment URLs (staging + production) kept always up to date.

## S5 — UI/UX Engineer & Frontend Support

Main Mission You make the product look and feel professional. The graduation committee will judge the platform in a 10-minute demo — first impressions dominate. A platform with a polished UI scores higher than a feature-rich one that looks like a homework assignment. Own that responsibility.

### Daily Tasks & Weekly Goals

- WEEK 1: Figma wireframes for all 12 screens (low-fidelity, approved by team). Set up Tailwind CSS + shadcn/ui in React project. Define design tokens (colors, fonts, spacing). Build base Arabic RTL layout wrapper.

- WEEK 2: Build shared component library: Button, Card, Input, Modal, Badge, Avatar, Navbar, Sidebar, PageLayout. All Arabic-ready.

- WEEK 3: Landing page (hero, social proof, CTAs, footer), Onboarding wizard UI (5 steps), Skill tag input component.

- WEEK 4: CV Builder UI (two-column: form + live preview + ATS score meter), Notification center UI, Profile edit page.

- WEEK 5: Mobile responsiveness review of ALL screens. Fix RTL layout issues. Support S2 on any complex screen that needs UI help.

- WEEK 6: Visual polish sprint — pixel-perfect review of every demo screen. Loading skeleton screens. Empty state designs. Error states.

### Final Deliverables — What Success Looks Like

- Component library: 15+ reusable components documented and used consistently across all screens.

- Landing page looks startup-quality — not student project quality.

- All screens work correctly in Arabic RTL on a 375px mobile screen.

- CV Builder shows real-time ATS score update as user types.

- Every screen has proper loading states — no white flash while data loads.

- Color, typography, and spacing consistent on every single page.

### Dependencies

- Gives to S2: Component library (import and use — no re-inventing).

- Gives to S3: CV Builder UI wired to receive ATS score data from AI engine.

- Receives from S1: API response structures (to design loading skeletons correctly).

- Receives from S3: ATS score data format (to build the score meter correctly).

# Section 4 — 6-Week Development Phase Plan

Each phase has clear outputs. A phase is NOT complete until its outputs are checked off. The team lead (S1) confirms phase completion each Friday.

## Phase 1 — Planning & Setup (Week 1)

Goal Zero ambiguity. Every student knows exactly what to build. All tools ready. No one blocked on Day 2.

| Who | Tasks | Output |
| --- | --- | --- |
| S1 | Create GitHub org + repos (backend + frontend + ai-service). Laravel project scaffold. Define DB schema. Write migrations for all core tables. Set up .env.example. Create API contract doc. | Repo setup, migrations committed, API contract v1 shared |
| S2 | React project with Vite. Install Zustand, React Router, Axios, i18next. Set up folder structure. Create AxiosClient with base URL. Wire up RTL Arabic layout. | Scaffolded React app running locally, RTL working |
| S3 | FastAPI project scaffold. PostgreSQL connection. /health endpoint. Research LanguageTool API. Plan recommendation feature vector schema. | FastAPI running locally, health endpoint responding |
| S4 | GitHub Actions: lint + test pipeline on PRs. Set up Railway (backend) + Vercel (frontend) staging. Write shared API contract template. | CI pipeline running, staging URLs shared with team |
| S5 | Figma wireframes for 12 screens (get team sign-off by Wednesday). Set up Tailwind + shadcn/ui in React. Define design token file (colors, fonts). | Approved wireframes, design token file committed |

Phase 1 Exit Criteria ✅ All 3 repos on GitHub with correct branch structure ✅ Backend runs locally, DB connected, migrations applied ✅ Frontend runs locally in Arabic RTL ✅ FastAPI runs locally with health endpoint ✅ CI pipeline green on staging PRs ✅ Team has agreed on all wireframes

## Phase 2 — Core Backend + Database (Week 2)

Goal All critical APIs live. Frontend can start consuming real data for auth and profiles.

| Who | Tasks | Output |
| --- | --- | --- |
| S1 | Auth API complete (register, login, OTP, role assignment, Sanctum tokens). Graduate profile CRUD API. Mentor profile API. Spatie RBAC configured. | Auth + Profile APIs tested in Bruno, documented |
| S2 | Build Graduate onboarding wizard (using S5 components). Build Mentor discovery page (cards with mock data). Hook auth forms to real S1 API. | Onboarding wizard + discovery page working with real auth |
| S3 | Recommendation engine v1: implement weighted cosine similarity. Accept graduate profile JSON, return ranked mentor list with scores. | POST /recommend working, tested with sample data |
| S4 | Build Admin: user list page + mentor verification queue. Write integration tests for Auth API (register → verify → login flow). | Admin user management working, Auth tests passing |
| S5 | Build component library: Button, Card, Input, Badge, Avatar, Navbar, Sidebar. All in Arabic RTL. Shared in repo /components/ui. | 15+ components committed and documented in Storybook/README |

Phase 2 Exit Criteria ✅ Can register as Graduate or Mentor and see correct dashboard ✅ Mentor discovery page shows 5+ mentor cards ✅ AI recommendation endpoint returns scored mentor list ✅ Admin can see user list and approve a mentor ✅ Component library committed and S2 using it

## Phase 3 — Frontend UI + APIs (Week 3)

Goal Booking system live. Core user journeys completable end-to-end.

| Who | Tasks | Output |
| --- | --- | --- |
| S1 | Booking API: create request, confirm, cancel, conflict detection. Availability slots API. Session list + detail API. Scheduling reminder queue (Laravel Scheduler + Queue). | Booking system fully functional via API |
| S2 | Booking flow UI: slot picker calendar → goal input → confirm. Session history dashboard. Graduate dashboard home with stats. Connect all to S1 real APIs. | Complete booking journey working in browser |
| S3 | CV ATS Engine: PDF parsing, keyword extraction, ATS scoring formula. Expose POST /cv/analyze. Test with 5 real CVs. | CV analyze endpoint working with score + keyword gaps |
| S4 | End-to-end test: Graduate registers → books session → mentor confirms. Write test for conflict detection (double booking). Deploy Phase 3 state to staging. | E2E test passing, staging updated |
| S5 | Landing page complete. Onboarding wizard visual polish. Profile edit page UI. Availability calendar component for mentor dashboard. | Landing page live on staging, profile pages polished |

Phase 3 Exit Criteria ✅ Graduate can complete full booking journey in one session ✅ Mentor receives notification and can confirm/reject ✅ CV ATS scoring returns a realistic score with feedback ✅ No critical bugs in the booking flow on staging ✅ Landing page is live on Vercel staging domain

## Phase 4 — AI Engines + Video Calls (Week 4)

Goal The impressive features work. AI recommendations display. Video sessions connect. Messaging is live.

| Who | Tasks | Output |
| --- | --- | --- |
| S1 | Wire S3 FastAPI to Laravel: call /recommend on graduate login, cache scores in Redis. Messaging API (send/receive). WebSocket events via Soketi (BookingConfirmed, MessageReceived, SessionStarting). | AI recommendations in DB, messaging API live, WebSocket events firing |
| S2 | Integrate WebRTC VideoRoom.jsx from S3 into session page. Real-time messaging UI with Laravel Echo. Connect AI recommendation cards to real scores from API. | Video session joinable, live chat working, AI recommendations displayed |
| S3 | Deliver VideoRoom.jsx React component (S2 integration). Grammar check via LanguageTool API. CV suggestions generator. Deploy FastAPI to Railway. | VideoRoom.jsx handed to S2, LanguageTool integrated, FastAPI on Railway |
| S4 | Test WebRTC: two browser sessions connect, video displays. Test WebSocket: send message, verify real-time delivery. Test AI: recommendation cards show correct mentors. | WebRTC and WebSocket integration tests passing |
| S5 | CV Builder UI: two-column layout with form + live preview. ATS score meter component (updates as user types). Notification bell + dropdown UI. | CV Builder fully interactive, notifications display in UI |

Phase 4 Exit Criteria ✅ Graduate dashboard shows AI-matched mentor recommendations with scores ✅ Two users can join a video session and see each other's video ✅ Real-time messages appear without page refresh ✅ CV Builder shows updating ATS score as user edits sections ✅ FastAPI running on Railway (not just local)

## Phase 5 — Testing + Integration + Polish (Week 5)

Goal Every user journey works end-to-end. Bugs found by QA are fixed. Platform looks demo-ready.

| Who | Tasks | Output |
| --- | --- | --- |
| S1 | Fix all API bugs from S4 bug reports. Optimize slow queries. Add DB indexes. Ensure all demo seed data is populated. API rate limiting. | Zero critical API bugs, DB seeded with realistic demo data |
| S2 | Replace all remaining mock API calls with real endpoints. Fix all state management edge cases. Ensure error states display properly on every screen. | No mock data in any screen — all real API data |
| S3 | Performance testing of AI endpoints — must respond <3s. Fix any recommendation quality issues. Final WebRTC stability testing. | AI endpoints <3s response time, WebRTC stable in poor network |
| S4 | Full regression test of all 5 user journeys. File GitHub Issues for every bug. Coordinate fixes. Deploy to production domain for first time. | Test report, production deployment live, zero P0 bugs |
| S5 | Mobile responsiveness audit of every screen. Fix RTL issues. Add skeleton loading screens. Polish typography and spacing inconsistencies. | Mobile-perfect UI, loading skeletons on all data-heavy pages |

Phase 5 Exit Criteria ✅ All 5 user journeys tested and passing (Graduate, Mentor, Admin, CV Builder, Video Session) ✅ Production domain live with SSL certificate ✅ Zero P0 (blocking) bugs in demo accounts ✅ Platform loads correctly on mobile (375px width) ✅ All screens have loading states — no blank white flashes

## Phase 6 — Final Demo & Deployment Preparation (Week 6)

Goal The platform is bulletproof for the 10-minute graduation demo. Everyone knows their role in the presentation.

| Who | Tasks | Output |
| --- | --- | --- |
| S1 | Final DB seeding with impressive demo data. Verify all production environment variables. Write a 'demo recovery script' to reset demo accounts if needed. | Production DB fully seeded, recovery script ready |
| S2 | Record a screen-capture backup demo video (in case of internet failure on demo day). Final walkthrough of all screens with team. Fix any last-minute UI bugs. | Backup demo video recorded, all screens signed off |
| S3 | Prepare 3 impressive demo scenarios for AI (show recommendation changing as profile changes). Ensure AI endpoints are warm (no cold-start delay). | AI demo scenarios scripted and tested 3 times |
| S4 | Final production deployment check. Test all demo accounts login. Verify domain, SSL, and all services healthy. Write platform test report for committee. | Platform test report document, all systems green on demo day |
| S5 | Final visual polish. Prepare demo presentation slides (10 slides max). Design demo script: who shows what, in what order. | Presentation slides done, demo script agreed by team |

# Section 5 — Smart Parallel Execution Strategy

The biggest risk in student teams is serialization — everyone waiting for one person to finish. This section eliminates that by defining exactly how the team runs in parallel from Day 1.

## The Mock API Pattern (Frontend Never Waits for Backend)

How It Works S2 and S5 never wait for S1 to finish APIs. They work with mock data files that mirror the exact JSON structure S1 documents in the API contract. When the real API is ready, changing one line (the base URL) switches from mock to real. This is professional development practice.

- Week 1: S1 writes the API contract (response shapes) before writing a single controller.

- Week 1: S2 creates /src/mocks/ folder with JSON files matching every API response.

- Week 1-3: S2/S5 build all UI using mock data via a toggleable USE_MOCK=true env variable.

- Week 3+: As S1 completes real endpoints, S2 switches each one from mock to real — one at a time.

- Week 5: USE_MOCK=false permanently. All screens run on real API.

## The Independent AI Service Pattern (S3 Never Blocks Anyone)

How It Works S3's FastAPI service is completely independent. S1 calls it via HTTP. S2 displays its results. S3 can develop at full speed without waiting for anyone. A shared endpoint contract (documented in Week 1) ensures everyone builds to the same interface.

## Parallel Work Map by Week

| Week | S1 (Backend) | S2 (Frontend) | S3 (AI/Video) | S4 (QA/Admin) | S5 (UI/UX) |
| --- | --- | --- | --- | --- | --- |
| 1 | DB Schema + Scaffold | React Scaffold + RTL | FastAPI Scaffold | CI/CD + Staging | Figma + Design Tokens |
| 2 | Auth + Profile APIs | Onboarding + Discovery (mock) | Recommend Engine v1 | Admin User List | Component Library |
| 3 | Booking + Scheduling APIs | Booking UI (mock → real) | CV ATS Engine | E2E Booking Test | Landing Page + Profile UI |
| 4 | AI wiring + Messaging + WS | Video Room + Chat UI | WebRTC + Grammar Check | WS + Video Tests | CV Builder UI |
| 5 | Bug fixes + DB seed | Replace all mocks | AI performance | Full regression | Mobile + Skeletons |
| 6 | Demo DB + recovery | Backup video + fixes | AI demo scenarios | Deploy + test report | Slides + script |

Golden Rule of Parallel Execution If your work is blocked by a teammate for MORE than 2 hours, escalate immediately in the team channel. Do not silently wait. Pivot to another task from your backlog while the blocker is resolved. Blocked time is wasted time — the team cannot afford it in a 6-week sprint.

# Section 6 — GitHub Collaboration Workflow

Clear Git rules prevent the most common team catastrophe: merge conflicts that consume days of debugging. Follow these rules without exception.

## Repository Structure

- alumni-compass-backend/ — Laravel API (S1 owns main branch)

- alumni-compass-frontend/ — React SPA (S2 owns main branch)

- alumni-compass-ai/ — FastAPI AI service (S3 owns main branch)

- All 3 repos under one GitHub Organization: alumni-compass

## Branch Strategy

| Branch | Purpose | Who Merges |
| --- | --- | --- |
| main | Production-ready code only. Deployed to production automatically. | S4 (after full testing) |
| staging | Integration branch. All feature branches merge here first. | Module lead after PR review |
| feature/[name] | Individual feature work. Branched from staging. Short-lived. | Create your own, merge via PR |
| hotfix/[name] | Urgent bug fixes on staging or main. Merge directly after review. | S1 or S2 depending on domain |

## Commit Naming Convention

Format: type(scope): short description feat(auth): add OTP verification endpoint fix(booking): resolve double-booking conflict detection bug style(dashboard): fix RTL alignment on mentor cards chore(ci): add PHP lint step to GitHub Actions test(booking): add integration test for cancel booking flow docs(api): update Bruno collection with booking endpoints Types: feat ¦ fix ¦ style ¦ chore ¦ test ¦ docs ¦ refactor ¦ perf Keep descriptions under 72 characters. Always reference an Issue # if one exists: 'fix(auth): resolve token expiry bug — closes #23'

## Pull Request Rules

- Every feature branch requires a PR before merging to staging — no direct pushes.

- PR must have: clear title, short description of what changed, screenshots if UI change.

- Minimum 1 reviewer approval required (the module lead for that domain).

- All CI checks must be green before merge — never merge a red PR.

- PR should be small — maximum 300 lines of code changed. Large changes = multiple smaller PRs.

- If PR is for an API endpoint: Bruno collection must be updated in the same PR.

## Folder Structure — Laravel Backend

alumni-compass-backend/ app/ Http/Controllers/Api/V1/ ← All API controllers Http/Requests/ ← Form Request validation classes Http/Resources/ ← API Resource transformers Services/ ← Business logic (BookingService, RecommendationService) Repositories/ ← Database query logic Events/ ← Laravel Events (BookingConfirmed, etc.) Listeners/ ← Event Listeners (SendBookingEmail, etc.) Jobs/ ← Queue Jobs (ProcessAIRecommendation, etc.) database/migrations/ ← All DB migrations database/seeders/ ← Demo data seeders routes/api.php ← All API routes (versioned)

## Folder Structure — React Frontend

alumni-compass-frontend/src/ components/ui/ ← shadcn/ui components (S5 owns) components/shared/ ← Shared business components (MentorCard, SessionCard) pages/ ← Page-level components (one file per route) graduate/ ← Graduate-specific pages mentor/ ← Mentor-specific pages admin/ ← Admin pages auth/ ← Login/Register/Onboarding pages hooks/ ← Custom React hooks (useWebRTC, useRecommendations) store/ ← Zustand state stores (authStore, sessionStore) api/ ← Axios API functions (one file per domain) mocks/ ← Mock JSON data (used until real API ready) utils/ ← Helper functions i18n/ ← Arabic/English translation files styles/ ← Global CSS, Tailwind config

# Section 7 — Daily Coordination System

The lightest-weight system that prevents surprises. No hour-long meetings. No bureaucracy. Just enough structure to keep 5 people synchronized.

## Daily Async Standup (10 Minutes Maximum)

The 3-Question Format — Posted in Team Chat Every Morning by 9:00 AM 1. DONE: What did I complete since yesterday? 2. TODAY: What will I complete by end of day? 3. BLOCKED: Is anything stopping me? (If yes, tag the relevant person immediately) If you have no blocker — great. If you do — it must be resolved by noon same day. Use WhatsApp group or Discord channel — whatever the team agrees on on Day 1.

## Weekly Rhythm

| Day | Activity | Owner |
| --- | --- | --- |
| Monday | Week kickoff — confirm tasks for each student for the week ahead | S1 (project lead) |
| Wednesday | Mid-week check: are we on track? Any phase slippage? Rebalance tasks if needed. | All team — 15-min video call |
| Friday | Phase review: what was committed for the week? What was delivered? What moves to next week? | S1 + S4 (lead + QA) |
| Friday | Deploy current state to staging after phase review | S4 |
| Sunday | Weekly async update posted: what changed in staging this week | S4 |

## Communication Rules

- Primary channel: WhatsApp/Discord group (team chooses on Day 1 — stick to one).

- GitHub Issues: ALL bugs reported here with labels (P0-critical, P1-high, P2-nice-to-have).

- API changes: S1 must post in team channel 24 hours before changing any existing API endpoint.

- If something will be late: announce it the night before, not on the deadline day.

- Never say 'I think it's working' — test it with a real scenario before marking done.

## Escalation Protocol

When Things Go Wrong Level 1 (2-hour block): Post in team chat. Someone should respond within 30 minutes. Level 2 (half-day block): Jump on a 15-minute video call. Pair-program if needed. Level 3 (full-day block): This is a project risk. S1 makes a scope decision — simplify the feature rather than stay blocked. Level 4 (multi-day block): De-scope the feature to MVP version. Document it as 'Phase 2'. Never let one feature sink the whole project.

# Section 8 — Speed & Risk Management Plan

## 8.1 Speed Accelerators — Use These from Day 1

### Pre-Built Packages (Don't Re-Invent These)

| What to Build | Use This Instead | Hours Saved |
| --- | --- | --- |
| RBAC from scratch | Spatie Laravel-Permission (composer) | 12+ hours |
| Calendar UI component | react-big-calendar or @schedule-x/react | 16+ hours |
| All UI components | shadcn/ui (CLI install per component) | 40+ hours |
| PDF generation | barryvdh/laravel-dompdf (composer) | 8+ hours |
| Email templates | Laravel Mail + Blade templates | 6+ hours |
| Real-time WS client | Laravel Echo + Soketi (npm install) | 10+ hours |
| Form validation | React Hook Form + Zod (npm install) | 8+ hours |
| Recommendation math | scikit-learn cosine_similarity (pip) | 20+ hours |
| PDF CV parsing | pdfplumber (pip install) | 10+ hours |
| Grammar checking | LanguageTool REST API (free) | 15+ hours |
| Notification system | Laravel Notifications + FCM package | 10+ hours |

## 8.2 AI Feature MVP Simplification

If the team runs behind schedule, here are pre-approved simplifications that preserve the demo value without the implementation complexity:

| Feature | Full Version (If Ahead) | MVP Version (If Behind) |
| --- | --- | --- |
| Recommendation Engine | Cosine similarity on full feature vector | Simple rule: match by major + target role field only |
| ATS Scoring | Full keyword + formatting + grammar score | Keyword matching only (count matches vs. job role keywords) |
| CV Grammar Check | Live LanguageTool API call | Show a fixed checklist of common CV writing tips |
| WebRTC Adaptive Bitrate | Dynamic quality switching on packet loss | Fixed 480p stream, manual audio-only toggle button |
| Career Roadmap | AI-generated personalized plan | Curated template plans per major (pre-written, selected by profile) |
| Messaging Real-Time | WebSocket with Echo | Simple polling (refresh every 10s) — looks same in demo |

When to Simplify Apply MVP simplification if a feature has been in progress for 3+ days without a working demo. Announce the simplification in the team channel. Document the full version plan for Phase 2. A simple, working feature ALWAYS beats a complex, broken one for a graduation demo.

## 8.3 Common Student Team Risks & Mitigations

| Risk | Warning Sign | Mitigation |
| --- | --- | --- |
| One student carries the whole project | Others ask 'what should I do?' after Week 2 | Section 3 ownership is non-negotiable. Hold everyone accountable. |
| Scope creep (adding features) | Team discusses new ideas in Week 4+ | Freeze feature scope after Week 3. New ideas go to a 'Phase 2' list. |
| Integration failure at Week 5 | Frontend and backend never tested together | Mandatory staging deploy every Friday from Week 2 onward. |
| S3 AI features break demo | AI returns wrong/empty data during demo | S3 pre-loads demo scenarios with hardcoded inputs guaranteed to return good output. |
| Demo day internet failure | Platform unreachable during presentation | S2 records a 5-minute full demo backup video in Week 6. |
| Git merge chaos | Multiple people editing same file | Branch discipline from Section 6 is mandatory. S4 enforces it. |
| Backend not ready for frontend | S2 idle waiting for S1 | Mock API pattern (Section 5) — S2 never waits. |
| Student burnout in Week 5 | Slipping daily standups, slow responses | Wednesday check-in flags this early. Rebalance workload, not timeline. |

# Section 9 — Final Pre-Demo Deliverables Checklist

This is the team's definition of done. Every item must be checked before standing in front of the graduation committee. S4 owns this checklist and signs off on each item.

## 9.1 Platform Functionality Checklist

### Authentication & Roles

- Graduate can register, receive OTP, log in, and see Graduate Dashboard.

- Mentor can register, submit verification docs, get approved by Admin, log in, see Mentor Dashboard.

- Admin can log in, see admin panel, approve/reject mentors, view all users.

- Role switching correctly restricts access — graduate cannot access admin routes.

### AI Mentor Recommendation

- Graduate dashboard displays top 5 AI-matched mentors with visible match scores.

- Mentor cards show: name, title, expertise tags, rating, match percentage, 'Book' button.

- Dismissing a mentor removes it from the list without page refresh.

- Recommendations are different for two graduates with different profiles (demonstrable).

### Session Booking

- Graduate can view mentor's available time slots in a calendar view.

- Graduate can submit a booking request with a session goal.

- Mentor receives notification and can confirm or reject the booking.

- Conflict detection works: cannot book a slot already taken.

- Both parties receive confirmation notification after acceptance.

### CV Builder + ATS Engine

- Graduate can fill CV form section by section.

- ATS score updates in real time (or on save) as sections are completed.

- Keyword gap panel shows missing keywords for selected target role.

- Graduate can export a downloadable PDF CV.

- Score improvement is demonstrable: go from 40 to 70+ by adding keywords.

### WebRTC Video Session

- Two users can join the same session room via unique room link.

- Both video feeds display correctly in the video room layout.

- Audio is transmitted clearly between both participants.

- Audio-only button works — disables video stream, keeps audio.

- Text chat sidebar works during the video session.

### Messaging & Notifications

- Graduate and Mentor can exchange real-time messages (no page refresh).

- Notification bell shows unread count. Dropdown shows recent notifications.

- Email notifications sent for: registration, booking confirmation, session reminder.

### Admin Dashboard

- Admin sees platform stats: total users, active sessions, CVs created.

- Mentor verification queue: admin can approve with one click.

- User list: searchable, filterable by role, with status indicators.

## 9.2 Technical Quality Checklist

- Platform loads at a real domain with valid HTTPS SSL certificate.

- Frontend Lighthouse performance score ≥ 75 on desktop.

- No console errors on any page in production build.

- All pages display correctly in Arabic RTL layout.

- Platform works on mobile screen (375px) — all buttons tappable, text readable.

- All images and assets load — no broken image icons visible.

- Loading states display on all pages that fetch data — no white flash.

- Error states display when API fails — not a blank page.

## 9.3 Demo Preparation Checklist

- Demo accounts created and tested: 1 Graduate, 1 Mentor, 1 Admin — credentials written down.

- Demo data seeded: 10 mentor profiles (complete, realistic), 5 graduate profiles, 3 completed sessions.

- Demo scenario scripted: 8-minute walk-through with clear hand-offs between team members.

- Backup demo video recorded (full 8-minute walk-through screen capture with narration).

- Recovery plan: if any feature fails live, team knows which backup to show instead.

- All team members know how to answer likely committee questions about technical choices.

- Demo computer tested: browser tabs pre-opened, accounts pre-logged-in.

## 9.4 Documentation Checklist

- README.md in each repo: setup instructions, environment variables, how to run locally.

- API documentation: Bruno/Postman collection exported and committed to repo.

- System architecture diagram: one-page visual showing how all services connect.

- Team contribution summary: what each student built (for committee attribution).

Final Team Commitment If every item on this checklist is checked, you will walk into that graduation presentation with a product you are genuinely proud of — one that solves a real problem, uses real AI, and demonstrates the skills of 5 engineers who built something that matters. Build it. Ship it. Be proud of it. — Alumni Compass Execution Blueprint v1.0